## BLANK - Gantt Chart
Gantt Chart
Project Title |  | SIMIK (Sistem Informasi Manajemen Inventaris Kantor)
Project Manager |  | Rifqi Hakim
Team |  | Niceguy
Date |  | 2026-03-03
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Inisiasi & Perencanaan
1.1 | Identifikasi masalah |  |  |  |  | 100%
1.2 | Studi literatur |  |  |  |  | 100%
1.3 | Analisis sistem berjalan |  |  |  |  | 100%
1.4 | Penentuan ruang lingkup |  |  |  |  | 100%
1.5 | Penyusunan proposal |  |  |  |  | 100%
2 | Analisis Kebutuhan
2.1 | Analisis kebutuhan fungsional |  |  |  |  | 100%
2.2 | Analisis kebutuhan non-fungsional |  |  |  |  | 100%
2.3 | SRS |  |  |  |  | 100%
3 | Perancangan Sistem
3.1 | USE CASE |  |  |  |  | 100%
3.2 | DFD dan Class Activity |  |  |  |  | 100%
3.3 | Flowchart |  |  |  |  | 100%
3.4 | Desain |  |  |  |  | 100%
4 | Perancangan Antarmuka
4.1 | Desain halaman Login |  |  |  |  | 100%
4.2 | Desain Dashboard |  |  |  |  | 100%
4.3 | Desain halaman Data Barang |  |  |  |  | 50%
4.4 | Desain Barang Masuk & Keluar |  |  |  |  | 50%
5. | Implementasi Modul Inti
5.1 | Setup environment |  |  |  |  | 0%
5.2 | Pembuatan modul login |  |  |  |  | 0%
5.3 | Pembuatan modul dashboard |  |  |  |  | 0%
5.4 | CRUD Data Barang |  |  |  |  | 0%
6 | Implementasi Modul Transaksi
6.1 | Modul Supplier |  |  |  |  | 0%
6.2 | Modul Barang Masuk |  |  |  |  | 0%
6.3 | Modul Barang Keluar |  |  |  |  | 0%
7 | Implementasi Laporan
7.1 | Modul laporan inventaris |  |  |  |  | 0%
7.2 | Validasi stok otomatis |  |  |  |  | 0%
7.3 | Penyempurnaan fitur |  |  |  |  | 0%
8 | Testing & Dokumentasi
8.1 | Pengujian sistem (blackbox testing) |  |  |  |  | 100%
8.2 | Perbaikan bug |  |  |  |  | 85%
8.3 | Dokumentasi screenshot |  |  |  |  | 0%
8.4 | Penyusunan laporan akhir |  |  |  |  | 0%
8.5 | Persiapan presentasi |  |  |  |  | 0%